## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Singireddy Sriharsha | 2026-01-05 | visa case_status showing NaN due to wrong mapping | Sprint 1 | Singireddy Sriharsha | User Interface | Corrected mapping logic and reloaded dataset | 2026-01-05 | Closed | Verified in preprocessing
2 | Singireddy Sriharsha | 2026-01-05 | categorical columns not encoding properly | Sprint 1 | Singireddy Sriharsha | Maintainability | Applied correct LabelEncoder fit_transform | 2026-01-05 | Closed | Checked using df.info()
3 | Singireddy Sriharsha | 2026-01-11 | correlation heatmap not displaying during EDA | Sprint 2 | Singireddy Sriharsha | Standards | Added plt.show() and fixed figsize | 2026-01-11 | Closed | Heatmap displayed
4 | Singireddy Sriharsha | 2026-01-13 | company_age showing negative ages | Sprint 2 | Singireddy Sriharsha | Logical | Fixed formula: 2025 - yr_of_estab | 2026-01-15 | Closed | Validated values
5 | Singireddy Sriharsha | 2026-01-16 | the correlation heatmap not given correct relationship between features | Sprint 2 | Singireddy Sriharsha | Maintainability | added coolwarm to automatically differentiate colors | 2026-01-17 | Closed | Colors displayed and differentiated
6 | Singireddy Sriharsha | 2026-01-20 | Random Forest giving inconsistent predictions | Sprint 3 | Singireddy Sriharsha | Maintainability | Reduced RF depth; compared all 3 models | 2026-01-20 | Closed | Best model given
7 | Singireddy Sriharsha | 2026-01-20 | Gradient Boosting MAE/RMSE too high due to wrong learning rate | Sprint 3 | Singireddy Sriharsha | Standards | Adjusted learning_rate and checked performance | 2026-01-21 | Closed | Error reduced and given correct
8 | Singireddy Sriharsha | 2026-01-24 | RMSE values showing mismatch due to incorrect test split repeat | Sprint 3 | Singireddy Sriharsha | Logical | Added fixed random_state=42 | 2026-01-24 | Closed | Consistent RMSE achieved
9 | Singireddy Sriharsha | 2026-01-29 | Drop-down fields showing white background causing UI mismatch | Sprint 4 | Singireddy Sriharsha | Maintainability | Updated CSS & applied theme-compatible appearance:none | 2026-01-29 | Closed | UI Corrected
10 | Singireddy Sriharsha | 2026-01-30 | History table not showing company age & wage category | Sprint 4 | Singireddy Sriharsha | Logical | Synced DB schema and added missing INSERT fields | 2026-01-30 | Closed | Working Perfectly
11 | Singireddy Sriharsha | 2026-01-31 | Prediction failing due to mismatch in model input features | Sprint 4 | Singireddy Sriharsha | Logical | Rearranged features to match model, added dummy column | 2026-01-31 | Closed | Model accepting inputs
12 | Singireddy Sriharsha | 2026-01-31 | All history records showing “Denied” for status | Sprint 4 | Singireddy Sriharsha | Maintainability | Fixed incorrect mapping for case_status during saving | 2026-01-31 | Closed | Correct status stored
13 | Singireddy Sriharsha | 2026-02-03 | Pop-up layout misaligned on some screens | Sprint 4 | Singireddy Sriharsha | Maintainability | Adjusted popup-card CSS width and padding | 2026-02-04 | Closed | Popup stable
14 | Singireddy Sriharsha | 2026-02-04 | Backend crashing due to missing field fast_processing | Sprint 4 | Singireddy Sriharsha | Logical | Added mapping + updated form + backend | 2026-02-05 | Closed | stable
15 | Singireddy Sriharsha | 2026-02-06 | Wrong processing time predictions due to missing input order | Sprint 4 | Singireddy Sriharsha | Maintainability | Reconstructed 14-feature input order | 2026-02-06 | Closed | Correct predictions generated
16 | Singireddy Sriharsha | 2026-02-07 | History page misaligned when values long | Sprint 4 | Singireddy Sriharsha | Maintainability | Table column spacing adjusted | 2026-02-08 | Closed | Table readable

## Sheet2
Logical
User Interface
Maintainability
Standards
Others